## Notes
Use the cloud adoption plan | Cloud adoption plan for the deployment to Azure DevOps - Cloud Adoption Framework ¦ Microsoft Docs
The cloud adoption plan organizes activities by activity type:
Epics: An epic represents an overall phase of the cloud adoption lifecycle.
Features: Features are used to organize specific objectives within each phase. For instance, migration of a specific workload is a feature.
User stories: User stories group work into logical collections of activities based on a specific goal.
Tasks: Tasks are the actual work to be done.
At each layer, activities are sequenced based on dependencies. Activities are linked to articles in the Cloud Adoption Framework to clarify the objective or task at hand.
The clearest view of the cloud adoption plan comes from the Epics backlog view. For help with the backlog view, see view a backlog. From the backlog view, it's easy to plan and manage the work required to complete the current phase of the adoption lifecycle.
Note: The current state of the cloud adoption plan focuses heavily on migration efforts. Tasks related to governance, innovation, or operations must be populated manually.
Align the cloud adoption plan
The overview pages for the Strategy methodology and the Plan methodology refer to the strategy and plan template. The template organizes the decisions and data points. The data points align the template for the cloud adoption plan with your specific plans for adoption. Consider completing the exercises in the Strategy methodology and the Plan methodology before your new project begins.
The following articles support alignment of the cloud adoption plan:
Workloads: To capture workloads that might be migrated or modernized, align features within the cloud migration epic. Add and modify those features to migrate your top 10 workloads.
Assets: Each asset (virtual machine, application, or data) is represented by the user stories under each workload. Add and modify those user stories to align with your digital estate.
Rationalization: As each workload is defined, the initial assumptions about that workload can be challenged. The workload might result in changes to the tasks under each asset.
Create release plans: Iteration paths establish release plans by aligning efforts with various releases and iterations.
Establish timelines: To define the start and end dates for each iteration, create a timeline to manage the overall project.
These five articles help with the alignment tasks required to start managing your adoption efforts. The next step gets you started on the alignment exercise.

## Cloud Adoption Plan
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | Assigned To | State | Tags
1 | Epic | Cloud Adoption Strategy |  |  |  |  | New | Strategy
11 | Feature |  | Define Adoption Strategy |  |  |  | New | Strategy
90 | User Story |  |  | Motivations |  |  | New | Strategy
91 | User Story |  |  | Business Outcomes |  |  | New | Strategy
92 | User Story |  |  | Business Case |  |  | New | Strategy
93 | User Story |  |  | First Adoption Project |  |  | New | Strategy
2 | Epic | Cloud Adoption Plan |  |  |  |  | New | Plan
10 | Feature |  | Define the Cloud Adoption Plan |  |  |  | New | Plan
86 | User Story |  |  | Digital Estate |  |  | New | Plan
87 | User Story |  |  | Initial organizational alignment |  |  | New | Plan
88 | User Story |  |  | Skills readiness plan |  |  | New | Plan
89 | User Story |  |  | Update this Cloud Adoption Plan |  |  | New | Plan
12 | Task |  |  |  | Prioritize workloads |  | New | Plan
13 | Task |  |  |  | Align assets to workloads |  | New | Plan
14 | Task |  |  |  | Define iterations and releases |  | New | Plan
15 | Task |  |  |  | Create timelines |  | New | Plan
3 | Epic | Cloud Ready |  |  |  |  | New | Ready
9 | Feature |  | Landing zone creation |  |  |  | New | Ready
82 | User Story |  |  | Azure Readiness Guide |  |  | New | Ready
83 | User Story |  |  | CAF Migrate Landing Zone blueprint |  |  | New | Ready
84 | User Story |  |  | Landing zone considerations |  |  | New | Ready
85 | User Story |  |  | Deploy the modified blueprint |  |  | New | Ready
4 | Epic | Cloud Innovation |  |  |  |  | New | Innovation
5 | Epic | Cloud Migration |  |  |  |  | New | Migration
6 | Feature |  | First Workload |  |  |  | New | First Workload
22 | Task |  |  | Azure Migration Guide |  |  | New | First Workload
34 | Task |  |  | Select the first workload |  |  | New | First Workload
45 | Task |  |  | Review Expanded Scope Checklist |  |  | New | First Workload
54 | Task |  |  | Review Best Practices |  |  | New | First Workload
63 | Task |  |  | Update the adoption plan |  |  | New | First Workload
7 | Feature |  | First Host |  |  |  | New | First Host
79 | User Story |  |  | Extend the landing zone for VMWare |  |  | New | First Host
28 | Task |  |  |  | Escalate private cloud privileges |  | New | First Host
29 | Task |  |  |  | Configure on-premises DNS for private cloud |  | New | First Host
67 | Task |  |  |  | Configure workload DNS and DHCP setup |  | New | First Host
80 | User Story |  |  | Migrate VMs |  |  | New | First Host
26 | Task |  |  |  | Prerequisites |  | New | First Host
30 | Task |  |  |  | Migrate ISOs and Templates |  | New | First Host
49 | Task |  |  |  | Migrate VMs using PowerCLI |  | New | First Host
50 | Task |  |  |  | Migrate VMs using NSX Layer 2 VPN |  | New | First Host
69 | Task |  |  |  | Migrate VMs using backup and disaster recovery tools |  | New | First Host
81 | User Story |  |  | Update migration assessment, decision tree, and tooling |  |  | New | First Host
27 | Task |  |  |  | Evaluate migration options used to migrate the first host |  | New | First Host
68 | Task |  |  |  | Update the migration tooling decision tree to reflect VMWare migration options |  | New | First Host
8 | Feature |  | Workload Template |  |  |  | New | Workload Template
70 | User Story |  |  | Prerequisites |  |  | New | Workload Template
19 | Task |  |  |  | Decisions |  | New | Workload Template
37 | Task |  |  |  | Roles and Responsibilities |  | New | Workload Template
57 | Task |  |  |  | Environment readiness (Landing Zone) |  | New | Workload Template
71 | User Story |  |  | Assess the workload |  |  | New | Workload Template
23 | Task |  |  |  | Evaluate workload and asset readiness |  | New | Workload Template
33 | Task |  |  |  | Architect workload |  | New | Workload Template
46 | Task |  |  |  | Estimate Cloud Costs |  | New | Workload Template
53 | Task |  |  |  | Migration tool choice(s) |  | New | Workload Template
64 | Task |  |  |  | Change approval process |  | New | Workload Template
72 | User Story |  |  | VM - UX Server |  |  | New | Workload Template
18 | Task |  |  |  | Assess |  | New | Workload Template
38 | Task |  |  |  | Migrate |  | New | Workload Template
43 | Task |  |  |  | Optimize workload(s) |  | New | Workload Template
56 | Task |  |  |  | Secure and Manage |  | New | Workload Template
59 | Task |  |  |  | Document configuration |  | New | Workload Template
73 | User Story |  |  | VM - Middle Tier |  |  | New | Workload Template
25 | Task |  |  |  | Assess |  | New | Workload Template
31 | Task |  |  |  | Migrate |  | New | Workload Template
48 | Task |  |  |  | Optimize workload(s) |  | New | Workload Template
51 | Task |  |  |  | Secure and Manage |  | New | Workload Template
66 | Task |  |  |  | Document configuration |  | New | Workload Template
74 | User Story |  |  | VM 3 - SQL Server |  |  | New | Workload Template
24 | Task |  |  |  | Assess |  | New | Workload Template
32 | Task |  |  |  | Migrate |  | New | Workload Template
47 | Task |  |  |  | Optimize workload(s) |  | New | Workload Template
52 | Task |  |  |  | Secure and Manage |  | New | Workload Template
65 | Task |  |  |  | Document configuration |  | New | Workload Template
75 | User Story |  |  | Test Workload |  |  | New | Workload Template
17 | Task |  |  |  | Set up Azure Monitor to track performance |  | New | Workload Template
39 | Task |  |  |  | Manual test with power users |  | New | Workload Template
42 | Task |  |  |  | Create/select automated test |  | New | Workload Template
60 | Task |  |  |  | Scale Test |  | New | Workload Template
76 | User Story |  |  | Optimize Workload Assets |  |  | New | Workload Template
16 | Task |  |  |  | Review test results |  | New | Workload Template
40 | Task |  |  |  | Decide on optimization timing |  | New | Workload Template
41 | Task |  |  |  | Adjust sizing |  | New | Workload Template
61 | Task |  |  |  | Document change |  | New | Workload Template
77 | User Story |  |  | Promote Workload |  |  | New | Workload Template
21 | Task |  |  |  | Network dependencies |  | New | Workload Template
35 | Task |  |  |  | Security Review |  | New | Workload Template
44 | Task |  |  |  | Governance Review |  | New | Workload Template
55 | Task |  |  |  | Final test |  | New | Workload Template
62 | Task |  |  |  | Promotion |  | New | Workload Template
78 | User Story |  |  | Decomission Retired Assets |  |  | New | Workload Template
20 | Task |  |  |  | Power down assets |  | New | Workload Template
36 | Task |  |  |  | Workload monitoring period |  | New | Workload Template
58 | Task |  |  |  | Decommission |  | New | Workload Template

## Strategy-Plan-Ready-Govern
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | State | Effort | Business Value | Value Area | Tags
94 | Epic | Cloud Adoption Strategy |  |  |  | New | 0 |  | Business | Strategy
101 | Feature |  | Define Adoption Strategy |  |  | New | 0 |  | Business | Strategy
306 | User Story |  |  | 1 - Motivations |  | New |  |  | Business | Strategy
307 | User Story |  |  | 2 - Business Outcomes |  | New |  |  | Business | Strategy
120 | Task |  |  |  | 1 - Sustainability targets and goals | New |  |  |  | Strategy
164 | Task |  |  |  | 2 - Sustainability reporting tool | New |  |  |  | Strategy
210 | Task |  |  |  | 3 - Implementation and application of OKRs (objectives, key results) | New |  |  |  | Strategy
308 | User Story |  |  | 3 - Business Case |  | New |  |  | Business | Strategy
254 | Task |  |  |  | 1 - Microsoft Cloud Economic Assessment | New |  |  |  | Strategy
309 | User Story |  |  | 4 - Adoption Project(s) |  | New |  |  | Business | Strategy
269 | Task |  |  |  | 1 - Build list of applications / workloads destined for Cloud | New |  |  |  | Strategy
310 | User Story |  |  | 5 - Who will deploy your environment. Self-build, Microsoft Services or Partner |  | New |  |  | Business | Strategy
95 | Epic | Cloud Adoption Plan |  |  |  | New | 0 |  | Business | Plan
100 | Feature |  | Build the Cloud Adoption Plan |  |  | New | 0 |  | Business | Plan
303 | User Story |  |  | 1 - Initial organizational alignment |  | New |  |  | Business | Plan
259 | Task |  |  |  | 3 - Map Skills needed for Cloud organization | New |  |  |  | Plan
262 | Task |  |  |  | 2 - Review skills needed for Cloud organization and build readiness plan | New |  |  |  | Plan
266 | Task |  |  |  | 1- Define team structures for the cloud. Cloud based organization | New |  |  |  | Plan
304 | User Story |  |  | 2 - Digital Estate |  | New |  |  | Business | Plan
121 | Task |  |  |  | 1 - App discovery & dependency mapping with Azure Migrate | New |  |  |  | Plan
166 | Task |  |  |  | 2 - Dependency Analysis with Azure Migrate | New |  |  |  | Plan
206 | Task |  |  |  | 3 - Dependency Analysis with AppDynamics | New |  |  |  | Plan
305 | User Story |  |  | 3 - Update the Cloud Adoption Plan |  | New |  |  | Business | Plan
282 | Task |  |  |  | 3 - Document Members of the Cloud Teams in Cloud Adoption Plan | New |  |  |  | Plan
283 | Task |  |  |  | 2 - Skills Readiness Plan for Developers, IT Staff and Business Users | New |  |  |  | Plan
284 | Task |  |  |  | 1 - Prioritize workloads and projects | New |  |  |  | Plan
96 | Epic | Cloud Ready |  |  |  | New | 0 |  | Business | Ready
98 | Feature |  | Getting Started with Azure |  |  | New | 0 |  | Business | Ready
318 | User Story |  |  | 1 - Azure Fundamentals |  | New |  |  | Business | Ready
168 | Task |  |  |  | 1 - How does Azure Work | New |  |  |  | Ready
170 | Task |  |  |  | 2 - Terminologies | New |  |  |  | Ready
171 | Task |  |  |  | 3 - Portfolio Hierarchy | New |  |  |  | Ready
172 | Task |  |  |  | 4 - Subscription purposes | New |  |  |  | Ready
173 | Task |  |  |  | 5 - Principles of Resource Groups | New |  |  |  | Ready
174 | Task |  |  |  | 6 - Azure administrative roles | New |  |  |  | Ready
175 | Task |  |  |  | 7 - Azure Monitoring and Security on Governance | New |  |  |  | Ready
176 | Task |  |  |  | 8 - Review Data Options | New |  |  |  | Ready
177 | Task |  |  |  | 9 - Review Storage Options | New |  |  |  | Ready
178 | Task |  |  |  | 10 - Review Network Options | New |  |  |  | Ready
179 | Task |  |  |  | 11 - Review Compute Options | New |  |  |  | Ready
180 | Task |  |  |  | 12 - Role-based Access Control | New |  |  |  | Ready
260 | Task |  |  |  | 13 - Azure for GCP Professionals | New |  |  |  | Ready
261 | Task |  |  |  | 13 - Azure for AWS Professionals | New |  |  |  | Ready
319 | User Story |  |  | 2 - Skills readiness plan |  | New |  |  | Business | Ready
115 | Task |  |  |  | 1 - Build a readiness plan and map roles | New |  |  |  | Ready
141 | Task |  |  |  | 2 - Microsoft Learn Platform | New |  |  |  | Ready
215 | Task |  |  |  | 3 - Microsoft Enterprise Skills Initiative | New |  |  |  | Ready
99 | Feature |  | Create the Landing zone, 3 potential paths: Enterprise Scale ¦ Start Small and Grow ¦ Partner built |  |  | New | 0 |  | Business | Ready
298 | User Story |  |  | 1 - Architectural Decision Guide |  | New |  |  | Business | Ready
130 | Task |  |  |  | 1 - Subscription Design | New |  |  |  | Ready
191 | Task |  |  |  | 2 - Subscription decision guides | New |  |  |  | Ready
285 | Task |  |  |  | 11 - Azure Naming and Tagging Convention | New |  |  |  | Ready
286 | Task |  |  |  | 10 - Automation and Planning for a DevOps approach | New |  |  |  | Ready
287 | Task |  |  |  | 9 - BCDR Design Considerations | New |  |  |  | Ready
288 | Task |  |  |  | 8 - Compliance and Policy Enforcement Decision Guide | New |  |  |  | Ready
289 | Task |  |  |  | 7 - Security Decision Guide and Best practices | New |  |  |  | Ready
290 | Task |  |  |  | 6 - Monitoring Decision Guide | New |  |  |  | Ready
291 | Task |  |  |  | 5 - Policy Enforcement Decision Guide | New |  |  |  | Ready
292 | Task |  |  |  | 4 - Network Decision Guide | New |  |  |  | Ready
293 | Task |  |  |  | 3 - Identity Decision Guide | New |  |  |  | Ready
299 | User Story |  |  | 2 - Landing zone considerations |  | New |  |  | Business | Ready
255 | Task |  |  |  | 4 - Evaluate Enterprise-Scale | New |  |  |  | Ready
256 | Task |  |  |  | 3 - Evaluate Terraform Landing Zone | New |  |  |  | Ready
257 | Task |  |  |  | 2 - Evaluate the CAF Foundation and Migrate Landing Zone blueprint | New |  |  |  | Ready
258 | Task |  |  |  | 1 - Decide on the path to create landing zone. Start Small and Growth, Enterprise Scale or Partner | New |  |  |  | Ready
300 | User Story |  |  | 3 - Create Azure Subscriptions |  | New |  |  | Business | Ready
119 | Task |  |  |  | 1 - EA Portal - Getting Started | New |  |  |  | Ready
137 | Task |  |  |  | 2 - Initial subscriptions | New |  |  |  | Ready
151 | Task |  |  |  | 3 - Scale subscriptions | New |  |  |  | Ready
154 | Task |  |  |  | 4 - Organize subscriptions | New |  |  |  | Ready
155 | Task |  |  |  | 5 - Organize Resources | New |  |  |  | Ready
165 | Task |  |  |  | 6 - Creating additional subscriptions | New |  |  |  | Ready
186 | Task |  |  |  | 7 - Associate or add an Azure subscription to you AAD Tenant | New |  |  |  | Ready
207 | Task |  |  |  | 8 - Creating Subscriptions Programmatically | New |  |  |  | Ready
212 | Task |  |  |  | 9 - Organizing resources with management groups | New |  |  |  | Ready
213 | Task |  |  |  | 10 - Tutorial: Create an additional Azure subscription | New |  |  |  | Ready
301 | User Story |  |  | 4 - Establish your Network |  | New |  |  | Business | Ready
105 | Task |  |  |  | 1 - Choose a networking architecture | New |  |  |  | Ready
106 | Task |  |  |  | 2 - Azure networking services overview | New |  |  |  | Ready
107 | Task |  |  |  | 3 - Common-Design-Principles-for-a-Hub-and-Spoke-VNET-Architecture | New |  |  |  | Ready
113 | Task |  |  |  | 4 - Hub and spoke network topology | New |  |  |  | Ready
122 | Task |  |  |  | 5 - Best Practices for Network Security | New |  |  |  | Ready
135 | Task |  |  |  | 6 - Network segmentation | New |  |  |  | Ready
152 | Task |  |  |  | 7 - Virtual Networking planning | New |  |  |  | Ready
153 | Task |  |  |  | 8 - Azure VPN Gateway | New |  |  |  | Ready
169 | Task |  |  |  | 9 - Create Virtual Networks | New |  |  |  | Ready
187 | Task |  |  |  | 10 - Create a Perimeter Network | New |  |  |  | Ready
209 | Task |  |  |  | 11 - Deploy highly available network virtual appliances | New |  |  |  | Ready
233 | Task |  |  |  | 12 - Tutorial: Create a Site to Site connection | New |  |  |  | Ready
236 | Task |  |  |  | 13 - Tutorial: Create a Point to Site VPN (OpenVPN) | New |  |  |  | Ready
238 | Task |  |  |  | 14 - Tutorial: Create a Point to Site VPN (Azure AD authentication) | New |  |  |  | Ready
239 | Task |  |  |  | 15 - Tutorial: Create a Point to Site VPN (Radius authentication) | New |  |  |  | Ready
240 | Task |  |  |  | 16 - Tutorial: Create a Point to Site VPN (Azure certificate authentication) | New |  |  |  | Ready
241 | Task |  |  |  | 17 - Tutorial: Create a Vnet to Vnet VPN | New |  |  |  | Ready
242 | Task |  |  |  | 18 - Tutorial: Create a Site to Site connection | New |  |  |  | Ready
243 | Task |  |  |  | 19 - Tutorial: Create and Manage a VPN Gateway | New |  |  |  | Ready
244 | Task |  |  |  | 20 - Tutorial: Connect virtual networks with virtual network peering using the Azure portal | New |  |  |  | Ready
245 | Task |  |  |  | 21 - Tutorial: Filter network traffic with a network security group using the Azure portal | New |  |  |  | Ready
302 | User Story |  |  | 5 - Identity and Access Management |  | New |  |  | Business | Ready
104 | Task |  |  |  | 1 - Identity Management Best Practices | New |  |  |  | Ready
116 | Task |  |  |  | 2 - Identity Access Management ¦ Least Privilege Access | New |  |  |  | Ready
139 | Task |  |  |  | 3 - Manage access to your Azure environment with role-based access controls | New |  |  |  | Ready
167 | Task |  |  |  | 4 - RBAC Roles | New |  |  |  | Ready
183 | Task |  |  |  | 5 - Secure resources with RBAC | New |  |  |  | Ready
188 | Task |  |  |  | 6 - Differences on RBAC Roles and Azure AD Roles | New |  |  |  | Ready
204 | Task |  |  |  | 7 - Tutorial: Add or remove role assignments using Azure RBAC and the Azure portal | New |  |  |  | Ready
247 | Task |  |  |  | 8 - Tutorial: Secure user sign-in events with Azure Multi-Factor Authentication | New |  |  |  | Ready
97 | Epic | Cloud Govern |  |  |  | New | 0 |  | Business | Govern
102 | Feature |  | Establish Governance Baseline & Governance Disciplines |  |  | New | 0 |  | Business | Govern
311 | User Story |  |  | 1 - Cloud Adoption Framework Governance Benchmark tool |  | New |  |  | Business | Govern
250 | Task |  |  |  | 1 - Cloud Adoption Framework Governance Benchmark Tool | New |  |  |  | Govern
251 | Task |  |  |  | 2 - AzGovViz (Azure Governance Visualizer), enables you to get insight into your Azure environment | New |  |  |  | Govern
312 | User Story |  |  | 2 - Identify business risks across apps, data and infrastructure |  | New |  |  | Business | Govern
280 | Task |  |  |  | 2 - Update Cloud Adoption Plan with risks and compliance requirements | New |  |  |  | Govern
281 | Task |  |  |  | 1 - Reference data for Control Mapping for specific compliance requirements | New |  |  |  | Govern
313 | User Story |  |  | 3 - Cost Management Discipline |  | New |  |  | Business | Govern
267 | Task |  |  |  | 4 - Define budgets and budget alerts | New |  |  |  | Govern
268 | Task |  |  |  | 3 - Identify accountability for billing and cost attribution | New |  |  |  | Govern
274 | Task |  |  |  | 2 - Update the Cloud Adoption Plan | New |  |  |  | Govern
279 | Task |  |  |  | 1 - Review the sample policies | New |  |  |  | Govern
314 | User Story |  |  | 4 - Resource Consistency Discipline |  | New |  |  | Business | Govern
273 | Task |  |  |  | 2 - Update the Cloud Adoption Plan | New |  |  |  | Govern
278 | Task |  |  |  | 1 - Review the sample policies | New |  |  |  | Govern
315 | User Story |  |  | 5 - Security Baseline Discipline |  | New |  |  | Business | Govern
265 | Task |  |  |  | 3 - Use the Azure Security Benchmark as the foundational security policy set | New |  |  |  | Govern
272 | Task |  |  |  | 2 - Update the Cloud Adoption Plan | New |  |  |  | Govern
277 | Task |  |  |  | 1 - Review the sample policies | New |  |  |  | Govern
316 | User Story |  |  | 6 - Identity Baseline Discipline |  | New |  |  | Business | Govern
271 | Task |  |  |  | 2 - Update the Cloud Adoption Plan | New |  |  |  | Govern
276 | Task |  |  |  | 1 - Review the sample policies | New |  |  |  | Govern
317 | User Story |  |  | 7 - Deployment Acceleration Discipline |  | New |  |  | Business | Govern
270 | Task |  |  |  | 2 - Update the Cloud Adoption Plan | New |  |  |  | Govern
275 | Task |  |  |  | 1 - Review the sample policies | New |  |  |  | Govern
335 | User Story |  |  | 8 - Data Governance |  | New |  |  | Business | Govern
252 | Task |  |  |  | 2 - Annotate your data | New |  |  |  | Govern
253 | Task |  |  |  | 1 - Classify data | New |  |  |  | Govern
103 | Feature |  | Tools to govern your Azure environment |  |  | New | 0 |  | Business | Govern
320 | User Story |  |  | 1 - Azure Active Directory Basics |  | New |  |  | Business | Govern
111 | Task |  |  |  | 1 - What is AAD | New |  |  |  | Govern
118 | Task |  |  |  | 2 - Compare AD with AAD | New |  |  |  | Govern
125 | Task |  |  |  | 3 - AAD Deployment Guide | New |  |  |  | Govern
129 | Task |  |  |  | 4 - Tutorial Create a new tenant in AAD | New |  |  |  | Govern
145 | Task |  |  |  | 5 - Tutorial: View your organization’s groups and members in AAD | New |  |  |  | Govern
146 | Task |  |  |  | 6 - Getting Started with Identity Governance | New |  |  |  | Govern
147 | Task |  |  |  | 7 - Enable MFA | New |  |  |  | Govern
148 | Task |  |  |  | 8 - Using security defaults | New |  |  |  | Govern
321 | User Story |  |  | 2 - Azure Policy |  | New |  |  | Business | Govern
149 | Task |  |  |  | 1 - Governance, security and compliance in Azure | New |  |  |  | Govern
182 | Task |  |  |  | 2 - Define IT compliance with Azure Policy | New |  |  |  | Govern
211 | Task |  |  |  | 3 - Organize policy with initiatives | New |  |  |  | Govern
214 | Task |  |  |  | 4 - Use policies to enforce standards | New |  |  |  | Govern
231 | Task |  |  |  | 5 - Tutorial: Create a policy assignment to identify non-compliant resources | New |  |  |  | Govern
322 | User Story |  |  | 3 - Resource Locks |  | New |  |  | Business | Govern
156 | Task |  |  |  | 1 - Use resource locks to protect resources (MS Learn) | New |  |  |  | Govern
160 | Task |  |  |  | 2 - Tutorial: Create a lock from Azure Portal | New |  |  |  | Govern
323 | User Story |  |  | 4 - Azure Blueprints |  | New |  |  | Business | Govern
114 | Task |  |  |  | 1 - Blueprint definitions | New |  |  |  | Govern
140 | Task |  |  |  | 2 - Define standard resources with Azure Blueprints | New |  |  |  | Govern
142 | Task |  |  |  | 3 - Azure Blueprint Samples | New |  |  |  | Govern
143 | Task |  |  |  | 4 - Azure Blueprints as code | New |  |  |  | Govern
144 | Task |  |  |  | 5 - Tutorial: Define and assign a blueprint in the portal | New |  |  |  | Govern
324 | User Story |  |  | 5 - Azure Service Health |  | New |  |  | Business | Govern
131 | Task |  |  |  | 1 - View service health notifications by using the Azure portal | New |  |  |  | Govern
134 | Task |  |  |  | 2 - Tutorial: Create activity log alerts on service notifications | New |  |  |  | Govern
325 | User Story |  |  | 6 - Azure Advisor |  | New |  |  | Business | Govern
132 | Task |  |  |  | 1 - Get started with Azure Advisor | New |  |  |  | Govern
133 | Task |  |  |  | 2 - Tutorial: Create Azure Advisor alerts on new recommendations | New |  |  |  | Govern
326 | User Story |  |  | 7 - Azure Cost Management |  | New |  |  | Business | Govern
157 | Task |  |  |  | 1 - Manage costs and billing for your Azure resources | New |  |  |  | Govern
158 | Task |  |  |  | 2 - What is Azure Cost Management and Billing? | New |  |  |  | Govern
159 | Task |  |  |  | 3 - How to optimize your cloud investment with Azure Cost Management | New |  |  |  | Govern
232 | Task |  |  |  | 4 - Tutorial: Create and manage Azure budgets | New |  |  |  | Govern
246 | Task |  |  |  | 5 - Tutorial: Create and manage exported data | New |  |  |  | Govern
248 | Task |  |  |  | 6 - Tutorial: Optimize costs from recommendations | New |  |  |  | Govern
249 | Task |  |  |  | 7 - Tutorial: Predict costs and optimize spending for Azure | New |  |  |  | Govern
327 | User Story |  |  | 8 - Azure Resource Graph |  | New |  |  | Business | Govern
194 | Task |  |  |  | 1 - Azure Resource Graph Explorer | New |  |  |  | Govern
195 | Task |  |  |  | 2 - Tutorial: Create and share an Azure Resource Graph query in the Azure portal | New |  |  |  | Govern
196 | Task |  |  |  | 3 - Starter Resource Graph query samples | New |  |  |  | Govern
197 | Task |  |  |  | 6 - Advanced Resource Graph query samples | New |  |  |  | Govern
198 | Task |  |  |  | 4 - Starter Resource Graph query samples | New |  |  |  | Govern
199 | Task |  |  |  | 5 - Advanced Resource Graph query samples | New |  |  |  | Govern
200 | Task |  |  |  | 7 - Understanding the Azure Resource Graph query language | New |  |  |  | Govern
201 | Task |  |  |  | 8 - Explore your Azure resources with Resource Graph | New |  |  |  | Govern
202 | Task |  |  |  | 9 - Azure Resource Graph security baseline for Azure Security Benchmark | New |  |  |  | Govern
203 | Task |  |  |  | 10 - Get resource changes | New |  |  |  | Govern
328 | User Story |  |  | 9 - Azure Monitor |  | New |  |  | Business | Govern
110 | Task |  |  |  | 1 - Manage Azure Monitor: Design a workspace deployment | New |  |  |  | Govern
128 | Task |  |  |  | 2 - Cloud monitoring guide: Monitoring strategy for cloud deployment models | New |  |  |  | Govern
163 | Task |  |  |  | 3 - Cloud monitoring guide: Collect the right data | New |  |  |  | Govern
192 | Task |  |  |  | 4 - Cloud monitoring guide: Alerting | New |  |  |  | Govern
217 | Task |  |  |  | 5 - Cloud monitoring guide: Monitoring platforms overview | New |  |  |  | Govern
221 | Task |  |  |  | 6 - Monitor Azure Service | New |  |  |  | Govern
222 | Task |  |  |  | 7 - Monitor resource groups | New |  |  |  | Govern
223 | Task |  |  |  | 8 - Logic Apps: How to trigger complex actions with Azure Monitor alerts | New |  |  |  | Govern
224 | Task |  |  |  | 9 - Monitoring Azure virtual machines with Azure Monitor | New |  |  |  | Govern
225 | Task |  |  |  | 10 - What is Azure Monitor for VMs | New |  |  |  | Govern
226 | Task |  |  |  | 11 - Tutorial: Monitor an Azure Virtual Machine with Azure Monitor | New |  |  |  | Govern
227 | Task |  |  |  | 12 - Azure Monitor for Containers | New |  |  |  | Govern
228 | Task |  |  |  | 13 - Logs querying: Log data ingestion time in Azure Monitor | New |  |  |  | Govern
229 | Task |  |  |  | 14 - Analyze your Azure infrastructure by using Azure Monitor logs (MS Learn) | New |  |  |  | Govern
230 | Task |  |  |  | 15 - Tutorial: Monitor an Azure resource with Azure Monitor | New |  |  |  | Govern
329 | User Story |  |  | 10 - Application Insights |  | New |  |  | Business | Govern
193 | Task |  |  |  | 1 - Azure Application Insights ¦ Getting Started with Application Insights | New |  |  |  | Govern
330 | User Story |  |  | 11 - Log Analytics |  | New |  |  | Business | Govern
108 | Task |  |  |  | 1 - Logs in Azure Monitor | New |  |  |  | Govern
123 | Task |  |  |  | 2 - Logs querying: Get started with log queries in Azure Monitor | New |  |  |  | Govern
136 | Task |  |  |  | 3 - Logs querying: Azure Monitor log queries | New |  |  |  | Govern
185 | Task |  |  |  | 4 - Logs querying: Tutorial - Create alert from log query | New |  |  |  | Govern
208 | Task |  |  |  | 5 - Logs querying: Azure Monitor log query examples | New |  |  |  | Govern
234 | Task |  |  |  | 6 - Logs querying: Writing efficient log queries | New |  |  |  | Govern
235 | Task |  |  |  | 7 - Activity Log: View and retrieve Azure Activity log events | New |  |  |  | Govern
237 | Task |  |  |  | 8 - Tutorial: Collect and analyze resource logs from an Azure resource | New |  |  |  | Govern
331 | User Story |  |  | 12 - Express Route |  | New |  |  | Business | Govern
109 | Task |  |  |  | 1 - Azure Express Route ¦ Tutorial: Connect a virtual network to an Express Route circuit | New |  |  |  | Govern
124 | Task |  |  |  | 2 - Azure Express Route ¦ Tutorial: Create and modify peering for an Express Route circuit | New |  |  |  | Govern
150 | Task |  |  |  | 3 - Azure Express Route ¦ Tutorial: Create and modify an Express Route circuit | New |  |  |  | Govern
181 | Task |  |  |  | 4 - Azure Express Route ¦ Prerequisites & Checklist | New |  |  |  | Govern
205 | Task |  |  |  | 5 - Azure Express Route ¦ Connectivity Models | New |  |  |  | Govern
332 | User Story |  |  | 14 - Network Watcher |  | New |  |  | Business | Govern
126 | Task |  |  |  | 1 - Network Insights (Preview) | New |  |  |  | Govern
161 | Task |  |  |  | 2 - Networking Analytics | New |  |  |  | Govern
189 | Task |  |  |  | 3 - DNS | New |  |  |  | Govern
219 | Task |  |  |  | 4 - Network Performance Monitor | New |  |  |  | Govern
220 | Task |  |  |  | 5 - Monitor and troubleshoot your end-to-end Azure network infrastructure by using network monitoring tools (MS Learn) | New |  |  |  | Govern
333 | User Story |  |  | 13 - Visualizing your data |  | New |  |  | Business | Govern
117 | Task |  |  |  | 1 - Visualizations: Create interactive reports with Azure Monitor workbooks | New |  |  |  | Govern
138 | Task |  |  |  | 2 - Visualizations: Create and share Azure Dashboards | New |  |  |  | Govern
184 | Task |  |  |  | 3 - Visualizations: Feed Power BI from Application Insights | New |  |  |  | Govern
216 | Task |  |  |  | 4 - Visualizations: Monitor your Azure services in Grafana | New |  |  |  | Govern
334 | User Story |  |  | 15 - Alerting |  | New |  |  | Business | Govern
112 | Task |  |  |  | 1 - Alerts: Improve incident response with alerting on Azure (MS Learn) | New |  |  |  | Govern
127 | Task |  |  |  | 2 - Alerts: Create, view and manage alerts based on Log Queries | New |  |  |  | Govern
162 | Task |  |  |  | 3 - Alerts: Create Metric Alerts for Logs in Azure Monitor | New |  |  |  | Govern
190 | Task |  |  |  | 4 - Alerts: Create, view and manage alerts based on Activity Log signals | New |  |  |  | Govern
218 | Task |  |  |  | 5 - Alerts: Creating action groups for notifications | New |  |  |  | Govern

## Server Migration
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | State | Effort | Business Value | Value Area | Tags
336 | Epic | CAF Server Migration Project Plan |  |  |  | New | 0 |  | Business
337 | Feature |  | 05 STAKEHOLDER SIGN OFF AND CLOSURE |  |  | New | 0 |  | Business
400 | User Story |  |  | CAF Server Migration Project Review and Clouser |  | New |  |  | Business
342 | Task |  |  |  | Sign off on Project delivery | New
343 | Task |  |  |  | Lessons Learnt documentation, Troubleshooting Guide for future supporting | New
344 | Task |  |  |  | Server Migration Project documentation and Supported documents review | New
345 | Task |  |  |  | Server Migration Project review meeting | New
338 | Feature |  | 04 CAF Migration Operation and Support |  |  | New | 0 |  | Business
401 | User Story |  |  | Monitoring and Reporting |  | New |  |  | Business
346 | Task |  |  |  | Documentation of monitoring and reporting process | New
347 | Task |  |  |  | Automation of reporting and alerting configuration | New
348 | Task |  |  |  | Configure Report Building | New
349 | Task |  |  |  | Configure Monitoring System | New
402 | User Story |  |  | Manage |  | New |  |  | Business
350 | Task |  |  |  | Cutover and Decommission | New
351 | Task |  |  |  | Protect and recover | New
352 | Task |  |  |  | Operational compliance | New
353 | Task |  |  |  | Inventory and visibility | New
339 | Feature |  | 03 CAF Server Migration Govern and Security |  |  | New | 0 |  | Business
403 | User Story |  |  | Govern |  | New |  |  | Business
354 | Task |  |  |  | Compliance | New
355 | Task |  |  |  | Security Implemtation and reporting | New
356 | Task |  |  |  | Governance | New
404 | User Story |  |  | Server Migration Transition |  | New |  |  | Business
357 | Task |  |  |  | Release Management | New
358 | Task |  |  |  | Transition to Support | New
359 | Task |  |  |  | Server migration Functional Validation | New
340 | Feature |  | 02 CAF Server Pre-Config & Migration |  |  | New | 0 |  | Business
405 | User Story |  |  | Migration of VMware to Azure |  | New |  |  | Business
360 | Task |  |  |  | Migration: Documentation of implementation and Change request for performing the activity | New
361 | Task |  |  |  | Test and Validate the VMWare Virtual server migration to Azure | New
362 | Task |  |  |  | Migrate VMWare Virtual Servers to Azure | New
363 | Task |  |  |  | Configure the Azure envirnment based on the assessment | New
364 | Task |  |  |  | Prepare the VMWare Virtual Server Assessment and requirement | New
406 | User Story |  |  | Migration of Hyper-V to Azure |  | New |  |  | Business
365 | Task |  |  |  | Test and Validate the Hyper V Host and Virtual server migration to Azure | New
366 | Task |  |  |  | Migrate Hyper V Host and Virtual Servers to Azure | New
367 | Task |  |  |  | Configure the Azure envirnment based on the assessment | New
368 | Task |  |  |  | Prepare the Hyper V Host and Virtual Server Assessment and requirement | New
407 | User Story |  |  | Migration of On-Prem to Azure |  | New |  |  | Business
369 | Task |  |  |  | Test and Validate the physical server migration to Azure | New
370 | Task |  |  |  | Migrate Physical Servers to Azure | New
371 | Task |  |  |  | Configure the Azure envirnment based on the assessment | New
372 | Task |  |  |  | Prepare the Physical Server Assessment and requirement | New
408 | User Story |  |  | Adopt-Migrate |  | New |  |  | Business
373 | Task |  |  |  | Migration: Application Integration | New
374 | Task |  |  |  | Migration: Infrastructure Integration | New
375 | Task |  |  |  | Migration: Deployment | New
376 | Task |  |  |  | Migration Strategy | New
377 | Task |  |  |  | Migration Pre-requirement configuration and validation | New
409 | User Story |  |  | Server Migration Pre-Configuration |  | New |  |  | Business
378 | Task |  |  |  | Cost and Billing of Azure resources | New
379 | Task |  |  |  | Site-to-Site Connectivity Summary | New
380 | Task |  |  |  | Azure Migration Readiness | New
381 | Task |  |  |  | Azure tools and Approaches | New
382 | Task |  |  |  | Managing Access | New
383 | Task |  |  |  | Azure Role Based Access | New
384 | Task |  |  |  | Azure Subscription target | New
385 | Task |  |  |  | Azure Cloud Resources | New
386 | Task |  |  |  | Azure Setup and Configuration | New
387 | Task |  |  |  | Prep on-prem Infrastructure | New
388 | Task |  |  |  | Create Pre-configuration documentation and Change Request | New
341 | Feature |  | 01 Plan, Assessment & Designing |  |  | New | 0 |  | Business
410 | User Story |  |  | Cloud Assessment |  | New |  |  | Business
389 | Task |  |  |  | Develop Cloud Adoption plan | New
390 | Task |  |  |  | Businesss logic and Infrastructure dependencies | New
391 | Task |  |  |  | Data requirement and Classification | New
392 | Task |  |  |  | Skills Readiness and Role Based Responsibilities | New
393 | Task |  |  |  | Organizational alignment to support the Adaption plan | New
411 | User Story |  |  | CAF Server Migration Design |  | New |  |  | Business
394 | Task |  |  |  | Planning, Assessement & Desiging review and SignOff | New
395 | Task |  |  |  | Security and Tisk Assessment | New
396 | Task |  |  |  | Network Topology Desiging | New
397 | Task |  |  |  | Detailed migration plan and effort documentation | New
412 | User Story |  |  | Define Strategy |  | New |  |  | Business
398 | Task |  |  |  | Inventory and Rationalize Digital Estate | New
399 | Task |  |  |  | Define Strategy CAF Plan Template | New

## SQL Migration
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | State | Effort | Business Value | Value Area | Tags
413 | Epic | Build the Plan |  |  |  | New | 0 |  | Business | Plan
415 | Feature |  | Strategy, Plan, Readiness |  |  | New | 0 |  | Business | Plan
466 | User Story |  |  | SQL Migration Readiness |  | New |  |  | Business | Plan
418 | Task |  |  |  | 1 - Azure Setup Guide | New |  |  |  | Plan
419 | Task |  |  |  | 2 - Create and/or Verify Landing Zone | New |  |  |  | Plan
420 | Task |  |  |  | 3 - Pros and Cons of Landing Zones and Migration Tools Decision Guide | New |  |  |  | Plan
421 | Task |  |  |  | 4 - Guide: Migrate SSIS, SSAS and SSRS to Azure | New |  |  |  | Plan
423 | Task |  |  |  | 5 - Reference Architectures | New |  |  |  | Plan
424 | Task |  |  |  | 6 - Tutorial: Azure SQL Fundamentals | New |  |  |  | Ready
427 | Task |  |  |  | 7 - Tutorial: Database migration to Azure | New |  |  |  | Ready
428 | Task |  |  |  | 8 - Tutorial: Migrate your relational data stored in SQL to Azure SQL DB | New |  |  |  | Ready
467 | User Story |  |  | Plan and Assessment |  | New |  |  | Business | Plan
429 | Task |  |  |  | 6 - Review Database Compatibility | New |  |  |  | Plan
452 | Task |  |  |  | 5 - Cloud Adoption plan | New |  |  |  | Plan
453 | Task |  |  |  | 4 - Skills Readiness Plan | New |  |  |  | Plan
454 | Task |  |  |  | 3 - Initial Organization Alignment | New |  |  |  | Plan
455 | Task |  |  |  | 2 - Align assets to cloud offerings to calculate pricing | New |  |  |  | Plan
456 | Task |  |  |  | 1 - Digital Estate: Collect Current Inventory with DMA | New |  |  |  | Plan
468 | User Story |  |  | Define Strategy |  | New |  |  | Business | Plan
434 | Task |  |  |  | 3 - Define Objectives and Key Results | New |  |  |  | Plan
457 | Task |  |  |  | 2 - Align SQL Migration project to business motivations | New |  |  |  | Plan
458 | Task |  |  |  | 1 - Review Cloud Adoption Plan | New |  |  |  | Plan
414 | Epic | SQL Migration |  |  |  | New | 0 |  | Business | Migrate
416 | Feature |  | CAF SQL Migration - Governance and Manage |  |  | New | 0 |  | Business | Govern
462 | User Story |  |  | SQL Migration - Governance |  | New |  |  | Business | Govern
430 | Task |  |  |  | 7 - Additional Resources for Governance | New |  |  |  | Govern
437 | Task |  |  |  | 6 - Monitoring and Reporting | New |  |  |  | Govern
438 | Task |  |  |  | 5 - Governance, Security and Compliance | New |  |  |  | Govern
439 | Task |  |  |  | 4 - Manage Costs | New |  |  |  | Govern
440 | Task |  |  |  | 3 - Manage Access | New |  |  |  | Govern
441 | Task |  |  |  | 2 - Organize resources | New |  |  |  | Govern
450 | Task |  |  |  | 1 - Manage Governance (Inventory / Operational Compliance) | New |  |  |  | Govern
417 | Feature |  | SQL Migration Scenarios and paths |  |  | New | 0 |  | Business | Migrate
463 | User Story |  |  | Migration - On-Prem to Azure SQL Managed Instance |  | New |  |  | Business | Migrate
431 | Task |  |  |  | 5 - Azure Quickstart SQL Managed Instance | New |  |  |  | Migrate
442 | Task |  |  |  | 4 - Release and Additional Resources | New |  |  |  | Migrate
443 | Task |  |  |  | 3 - Deployment and Migration Testing | New |  |  |  | Migrate
444 | Task |  |  |  | 2 - Assessment | New |  |  |  | Migrate
445 | Task |  |  |  | 1 - OnPrem to Azure SQL Managed Instance | New |  |  |  | Migrate
464 | User Story |  |  | Migration - On-Prem to Azure SQL Database |  | New |  |  | Business | Migrate
422 | Task |  |  |  | 1 - Assessment | New |  |  |  | Migrate
425 | Task |  |  |  | 2 - Deployment and Migration Testing | New |  |  |  | Migrate
426 | Task |  |  |  | 3 - Release and Additional Resources | New |  |  |  | Migrate
432 | Task |  |  |  | 4 - Azure Quickstart SQL Database | New |  |  |  | Migrate
465 | User Story |  |  | Migration of On-Prem to Azure VM |  | New |  |  | Business | Migrate
433 | Task |  |  |  | 5 - Azure Quickstart for SQL VMs | New |  |  |  | Migrate
446 | Task |  |  |  | 4 - Release and Additional Resources | New |  |  |  | Migrate
447 | Task |  |  |  | 3 - Deployment and Migration Testing | New |  |  |  | Migrate
448 | Task |  |  |  | 2 - Assessment | New |  |  |  | Migrate
449 | Task |  |  |  | 1 - OnPrem to Azure Virtual Machine Overview | New |  |  |  | Migrate

## Governance Readiness
ID | Work Item Type | Title 1 | Title 2 | State | Story Points | Value Area | Iteration Path | Tags
622 | User Story | 1 - Azure Fundamentals |  | New |  | Business | \
496 | Task |  | 4 - Subscription purposes | New |  |  | \
498 | Task |  | 8 - Microsoft Learn: Azure Fundamentals Learning Path | New |  |  | \
500 | Task |  | 7 - Azure Monitoring and Security on Governance | New |  |  | \
503 | Task |  | 6 - Azure administrative roles | New |  |  | \
504 | Task |  | 5 - Subscription decision guides | New |  |  | \
505 | Task |  | 3 - Portfolio Hierarchy | New |  |  | \
507 | Task |  | 1 - How does Azure Work | New |  |  | \
516 | Task |  | 2 - Terminologies | New |  |  | \
623 | User Story | 2 - Azure Active Directory Basics |  | New |  | Business | \
472 | Task |  | 1 - What is AAD | New |  |  | \
474 | Task |  | 2 - Compare AD with AAD | New |  |  | \
476 | Task |  | 3 - AAD Deployment Guide | New |  |  | \
478 | Task |  | 4 - Tutorial Create a new tenant in AAD | New |  |  | \
479 | Task |  | 5 - Tutorial: View your organization’s groups and members in AAD | New |  |  | \
482 | Task |  | 6 - Enable MFA | New |  |  | \
484 | Task |  | 7 - Tutorial: Secure user sign-in events with Azure Multi-Factor Authentication | New |  |  | \
485 | Task |  | 8 - Using security defaults | New |  |  | \
624 | User Story | 3 - Resources Organization |  | New |  | Business | \
499 | Task |  | 5 - Organize subscriptions and resources | New |  |  | \
506 | Task |  | 1 - Initial subscriptions | New |  |  | \
510 | Task |  | 4 - Associate or add an Azure subscription to you AAD Tenant | New |  |  | \
511 | Task |  | 3 - Tutorial: Create an additional Azure subscription | New |  |  | \
523 | Task |  | 2 - Scale subscriptions | New |  |  | \
625 | User Story | 4 - Role Based Access Control |  | New |  | Business | \
473 | Task |  | 1 - What is RBAC | New |  |  | \
475 | Task |  | 2 - Manage access to your Azure environment with role-based access controls | New |  |  | \
477 | Task |  | 3 - Role-based access control | New |  |  | \
480 | Task |  | 4 - Secure resources with RBAC | New |  |  | \
481 | Task |  | 5 - Tutorial: Add or remove role assignments using Azure RBAC and the Azure portal | New |  |  | \
483 | Task |  | 6 - Differences on RBAC Roles and Azure AD Roles | New |  |  | \
626 | User Story | 5 - Azure Policy |  | New |  | Business | \
494 | Task |  | 5 - Use policies to enforce standards | New |  |  | \
508 | Task |  | 4 - Organize policy with initiatives | New |  |  | \
513 | Task |  | 3 - Define IT compliance with Azure Policy | New |  |  | \
519 | Task |  | 2 - Governance, security and compliance in Azure | New |  |  | \
526 | Task |  | 1 - What is Azure Policy | New |  |  | \
621 | Task |  | 6 - Tutorial: Create a policy assignment to identify non-compliant resources | New |  |  | \
627 | User Story | 6 - Resource Locks |  | New |  | Business | \
520 | Task |  | 2 - Use resource locks to protect resources (MS Learn) | New |  |  | \
525 | Task |  | 1 - Lock resources to prevent unexpected changes | New |  |  | \
620 | Task |  | 3 - Tutorial: Create a lock from Azure Portal | New |  |  | \
628 | User Story | 7 - Azure Blueprints |  | New |  | Business | \
514 | Task |  | 3 - Define standard resources with Azure Blueprints | New |  |  | \
518 | Task |  | 2 - Blueprint definitions | New |  |  | \
527 | Task |  | 1 - What is Azure Blueprints? | New |  |  | \
618 | Task |  | 4 - Tutorial: Define and assign a blueprint in the portal | New |  |  | \
629 | User Story | 8 - Azure Service Health |  | New |  | Business | \
521 | Task |  | 2 - View service health notifications by using the Azure portal | New |  |  | \
524 | Task |  | 1 - What is Azure Service Health? | New |  |  | \
619 | Task |  | 3 - Tutorial: Create activity log alerts on service notifications | New |  |  | \
630 | User Story | 9 - Azure Advisor |  | New |  | Business | \
515 | Task |  | 3 - Get started with Azure Advisor | New |  |  | \
517 | Task |  | 2 - Introduction to Azure Advisor | New |  |  | \
528 | Task |  | 1 - Monitoring and reporting in Azure (CAF) | New |  |  | \
617 | Task |  | 4 - Tutorial: Create Azure Advisor alerts on new recommendations | New |  |  | \
631 | User Story | 10 - Azure Cost Management |  | New |  | Business | \
495 | Task |  | 5 - Tutorial: Create and manage Azure budgets | New |  |  | \
501 | Task |  | 7 - Tutorial: Optimize costs from recommendations | New |  |  | \
502 | Task |  | 6 - Tutorial: Create and manage exported data | New |  |  | \
509 | Task |  | 4 - Quickstart: Explore and analyze costs with cost analysis | New |  |  | \
512 | Task |  | 3 - How to optimize your cloud investment with Azure Cost Management | New |  |  | \
522 | Task |  | 2 - What is Azure Cost Management and Billing? | New |  |  | \
529 | Task |  | 1 - Manage costs and billing for your Azure resources | New |  |  | \
616 | Task |  | 8 - Predict costs and optimize spending for Azure | New |  |  | \
632 | User Story | 11 - Azure Resource Graph |  | New |  | Business | \
486 | Task |  | 1 - What is Azure Resource Graph? | New |  |  | \
487 | Task |  | 2 - Azure Resource Graph Explorer | New |  |  | \
488 | Task |  | 3 - Tutorial: Create and share an Azure Resource Graph query in the Azure portal | New |  |  | \
489 | Task |  | 4 - Starter Resource Graph query samples | New |  |  | \
490 | Task |  | 5 - Advanced Resource Graph query samples | New |  |  | \
491 | Task |  | 6 - Understanding the Azure Resource Graph query language | New |  |  | \
492 | Task |  | 7 - Explore your Azure resources with Resource Graph | New |  |  | \
493 | Task |  | 8 - Azure Resource Graph security baseline for Azure Security Benchmark | New |  |  | \
497 | Task |  | 9 - Get resource changes | New |  |  | \
633 | User Story | 12 - Tools and Additional Documents |  | New |  | Business | \
530 | Task |  | 11 - Governance Implementation Matrix V1 | New |  |  | \
531 | Task |  | 10 - Azure Management Subscription Architecture Sample V1 | New |  |  | \
532 | Task |  | 9 - Azure Networking Cloud Architecture Sample V1 | New |  |  | \
533 | Task |  | 8 - Azure Cloud Architecture Shared Business Unit Model Sample V1 | New |  |  | \
534 | Task |  | 7 - Enterprise Scale Architecture | New |  |  | \
535 | Task |  | 6 - CAF - Governance Playbook V2 | New |  |  | \
536 | Task |  | 5 - Cloud Adoption Framework One Pager | New |  |  | \
537 | Task |  | 4 - CAF - Cloud Adoption Framework Overview | New |  |  | \
538 | Task |  | 3 - CAF - Azure Account Organization and Governance | New |  |  | \
539 | Task |  | 2 - AzGovViz (Azure Governance Visualizer) | New |  |  | \
540 | Task |  | 1 - Cloud Adoption Framework Governance Benchmark Tool | New |  |  | \